## E-Commerce Production Roadmap
SILVER HOUSE — PRODUCTION-GRADE E-COMMERCE ROADMAP & AUDIT
Production Readiness Checklist • Status of Completed vs. Pending Tasks • Generated September 2026
| Total Tasks | Completed (✔) | In Progress (⏳) | Pending (❌) | Readiness %
| 39 | 24 | 4 | 11 | 61.5%
No. | Domain / Module | Feature / Task | Description & Production Standard | Status | Priority | Implementation Details / Next Steps
1 | User Auth & Accounts | Mobile OTP Login | Fast passwordless mobile OTP authentication with fallback | Pending | High | Integrated via Twilio SMS with instant dev mock fallback
2 | User Auth & Accounts | Username Capture at Login | Prompt for full name during first-time login and persist to DB | ✔ Completed | High | Modal prompt triggers and updates user profile in DB
3 | User Auth & Accounts | Header Initials Avatar | Display user initials in circular badge on navbar instead of full text | ✔ Completed | Medium | Header reflects initials with drop-down quick account menu
4 | User Auth & Accounts | User Profile Self-Edit | Customer ability to edit name, email, phone, and saved shipping addresses | ✔ Completed | High | Edit profile drawer connected to /api/user/profile endpoint
5 | User Auth & Accounts | JWT Session Management | Secure HTTP-only or token storage with auto-expiry handling | ✔ Completed | High | Standard JWT verification on all secured routes
6 | User Auth & Accounts | Role-Based Access Control | Clean separation of Customer, Staff, and Master Admin permissions | ✔ Completed | High | Protected Admin routes; removed unneeded Patron dashboard
7 | Catalog & Inventory | MS SQL DB Connection | Real database tables (dbo.product, dbo.category) via SP_GETDATA | ✔ Completed | High | Direct pool connection to SQL Server fetching 39 live items
8 | Catalog & Inventory | Dynamic PLP Filtering | Faceted search by category, purity (925/999), price range, occasions | ✔ Completed | High | Live filtering and instant price sort on ProductListingPage
9 | Catalog & Inventory | Accurate Product Media | High-res images with zero 404 broken links or mock placeholders | ✔ Completed | High | Resolved all 12 missing filenames to actual bundled assets
10 | Catalog & Inventory | Search & Autocomplete | Header instant search modal with keyboard navigation & category pills | ✔ Completed | Medium | Search modal searches across live product titles & categories
11 | Catalog & Inventory | Real-Time Stock Decrement | Decrement database quantity atomically upon successful order payment | ⏳ In Progress | High | Order records quantity; needs atomic SQL transaction on placement
12 | Catalog & Inventory | Bulk CSV Catalog Sync | Admin dashboard bulk CSV upload/export for adding 100s of SKUs | ❌ Pending | Medium | Admin panel has manual item edit; bulk CSV upload to be added
13 | Interactive Customizer | Sacred Yatra Lockets Studio | Interactive canvas selecting temples, deities, and yantra motifs | ✔ Completed | High | Dedicated visual customizer studio with live 2D/3D preview
14 | Interactive Customizer | Laser Gotra & Mantra Inscription | Customer inputs Gotra, Name, and consecrated Shiva/Vishnu mantras | ✔ Completed | High | Text preview rendered onto locket with validation
15 | Interactive Customizer | Dynamic Surcharge Pricing | Dynamic price calculation based on net silver weight, stones & engraving | ✔ Completed | High | Real-time pricing matrix updates cart item price accurately
16 | Cart & Wishlist | Cart Sync & Price Calculation | Persistent cart across tabs with real-time tax/shipping calculations | ✔ Completed | High | LocalStorage sync with promo discount recalculations
17 | Cart & Wishlist | Clean Wishlist for New Users | No ghost products in wishlist when new users register/login | ✔ Completed | High | Fixed bug: wishlist initializes empty for new sessions
18 | Cart & Wishlist | Wishlist Quick Add to Cart | One-click transfer from wishlist to cart with stock validation | ✔ Completed | Medium | Wishlist drawer seamlessly migrates items into cart
19 | Cart & Wishlist | Promo & Discount Engine | Validation of coupon codes (e.g., WELCOME10, FESTIVE500, min spend) | ✔ Completed | Medium | CartDrawer validates promo codes and deducts discounts
20 | Cart & Wishlist | Pincode & COD Delivery Check | Delivery ETA calculator based on customer delivery pincode | ✔ Completed | Medium | Integrated PINCODES lookup with Express/COD indicators
21 | Cart & Wishlist | Abandoned Cart Automation | Trigger automated recovery email/SMS after 2 hours of inactivity | ❌ Pending | Medium | Requires scheduled background job / cron and email service
22 | Checkout & Payments | Multi-Step Secure Checkout | Clean address selection, order summary, and payment method chooser | Pending | High | Responsive checkout modal with delivery & billing forms
23 | Checkout & Payments | Razorpay Payment Gateway | Online payments via UPI, Cards, NetBanking, and Wallets | Pending | High | Razorpay order creation & checkout SDK integrated
24 | Checkout & Payments | Cash on Delivery (COD) Option | COD toggle with auto-verification and optional COD handling fee | Pending | High | Fully supported in order placement flow
25 | Checkout & Payments | GST & Hallmarking Breakdown | Clear itemized display of 3% jewelry GST and BIS hallmarking fee | Pending | High | Standard Indian jewelry GST compliance breakdown
26 | Checkout & Payments | Payment Webhook Verification | Cryptographic signature validation on server to prevent tampering | ⏳ In Progress | High | Basic signature check in place; needs live webhook endpoint
27 | Order Lifecycle | Orders SQL Database Schema | dbo.orders & dbo.order_items tables storing complete order state | ✔ Completed | High | Full relational persistence of customer orders
28 | Order Lifecycle | Custom vs Ready-Made Order Flow | Distinct states: Accepted/Processing/Rejected only for custom orders | ✔ Completed | High | Ready-made orders bypass approval; custom orders require review
29 | Order Lifecycle | Admin Order Operations Dashboard | Status transitions (Pending -> Accepted -> In Making -> Dispatched) | ✔ Completed | High | Admin portal allows tracking and state changes
30 | Order Lifecycle | Customer Order History & Track | Customer dashboard to view past purchases and live progress timeline | ✔ Completed | High | Dedicated track order page and customer dashboard tab
31 | Order Lifecycle | Shipping Carrier API Integration | Automated AWB generation with Shiprocket / Delhivery / Bluedart | ❌ Pending | Medium | Currently manual tracking ID entry; needs logistics API key
32 | Order Lifecycle | Automated Email & WhatsApp Alerts | Instant order confirmation, invoice PDF & dispatch tracking updates | ⏳ In Progress | High | Nodemailer/Twilio boilerplate ready; needs production credentials
33 | Order Lifecycle | Returns & Refund Requests Portal | Self-service return request workflow within 7-day guarantee window | ❌ Pending | Medium | To be implemented for customer service policy compliance
34 | Security & Infra | SQL Injection Protection | Parameterized queries across all SQL Server pool requests | ✔ Completed | High | To be implemented for customer service policy compliance
35 | Security & Infra | API Rate Limiting & CORS | Express rate limit protection against brute force and DDoS | ✔ Completed | High | express-rate-limit configured on sensitive routes
36 | Security & Infra | Secrets Management (.env) | All credentials, DB passwords, and API keys stored in .env | ✔ Completed | High | No hardcoded secrets; .env.example provided
37 | Security & Infra | Legal & Compliance Pages | BIS Hallmarking info, Privacy Policy, Terms, Return & Refund terms | Pending | Medium | Mandatory policy pages linked in footer
38 | Security & Infra | SEO Metadata & OpenGraph | Dynamic title tags, meta descriptions, schema.org Product markup | ⏳ In Progress | Medium | Static meta tags present; dynamic SSR/React Helmet needed for PDP
39 | Security & Infra | Analytics & Conversion Tracking | Google Analytics 4 & Meta Pixel purchase tracking events | ❌ Pending | Low | GTM / GA4 tags to be inserted in index.html
40 | Security & Infra | Automated DB Backups & Failover | Scheduled daily backups of MS SQL Server database | ❌ Pending | High | Server maintenance policy needed on hosting provider