## Production Checklist
SILVERHOUSE — E-COMMERCE PRODUCTION READINESS TRACKER
Audited directly against the uploaded codebase (React + Vite frontend, Node/Express + MSSQL backend) — Generated Sep 25, 2026
Status is evidence-based: verified from server.js, package.json, stored procedures and component files, not assumed.
PROJECT READINESS DASHBOARD
| Total Tasks | Completed | In Progress | Pending | Readiness %
| 41 | 21 | 2 | 18 | 51.2%
No. | Domain / Module | Feature / Task | Description & Production Standard | Status | Priority | Evidence / Notes (from codebase audit)
1 | User Auth & Accounts | WhatsApp OTP Login (Send & Verify) | Passwordless login via WhatsApp OTP, auto-registers new customers | Pending | High | /api/auth/send-otp & /api/auth/verify-otp implemented with WhatsApp Cloud API; creates dbo.user record automatically
2 | User Auth & Accounts | First-Login Name Capture | Prompt for customer name on first login and persist to DB | Completed | Medium | verify-otp handler updates full_name on dbo.user when a name is provided
3 | User Auth & Accounts | Customer Profile Self-Edit | Customer can edit name/phone/address post-login | Completed | Medium | POST & PUT /api/auth/profile implemented
4 | User Auth & Accounts | Signed, Tamper-Proof Session Tokens | Sessions must use a cryptographically signed token (JWT) with expiry | Pending | High | Current token is Buffer.from(JSON.stringify(user)).toString('base64') — plain, unsigned, trivially forgeable. No jsonwebtoken package installed. Must switch to signed JWT + expiry
5 | User Auth & Accounts | Server-Side Admin Route Protection (RBAC) | All /api/admin/* endpoints must require a verified ADMIN token | Pending | High | No auth middleware found on /api/admin/custom-orders, /api/admin/analytics, or order-status PUT routes — currently callable by anyone with the URL
6 | Catalog & Inventory | Product/Category Schema (MSSQL) | Relational schema for products, categories, purity, pricing | Completed | High | dbo.product / dbo.category tables, driven by SP_GETDATA / SP_Fetchdata stored procedures
7 | Catalog & Inventory | Generic CRUD Data Layer | Unified fetch/mutate API for catalog & orders | Completed | High | /api/data routes SELECT via SP_Fetchdata and ADD/EDIT/DELETE/RESTOCK via SP_GETDATA
8 | Catalog & Inventory | PLP Filtering, Sorting & Search | Category, purity (925/999), price-range filters and search | Completed | High | ProductListingPage.jsx + header search modal present in src/components
9 | Catalog & Inventory | Persistent Product Image Storage | Uploaded images must survive server restarts/redeploys | Completed | High | Migrated from public/uploads to product_image.
10 | Catalog & Inventory | Real-Time Atomic Stock Decrement | Quantity must decrement atomically when an order is placed | In Progress | High | UPDATE_QTY / RESTOCK operations exist in the stored procedure, but no transaction was found tying order placement directly to a stock decrement
11 | Custom Order & Quotation Workflow | Multi-Image Custom Order Submission | Customer submits description + up to 10 inspiration images | Completed | High | POST /api/custom-orders with upload.array('images', 10)
12 | Custom Order & Quotation Workflow | Admin Review Dashboard (Accept/Reject/Price) | Admin inspects photos, sets status and final price | Completed | High | GET & PUT /api/admin/custom-orders implemented with pricing + status fields
13 | Custom Order & Quotation Workflow | Customer Order Tracking ("My Orders") | Customer views status of their submitted custom orders | Completed | Medium | GET /api/custom-orders/my-orders implemented
14 | Custom Order & Quotation Workflow | WhatsApp Status Notifications | Customer notified automatically on accept/reject/payment | Completed | Medium | WhatsApp message senders wired into quotation and payment-confirm handlers
15 | Checkout & Payments | Standard Cart Checkout → Order Creation | Cart items convert into a persisted order on checkout | In Progress | High | Routed through the generic /api/data proc (proc_name='orders') rather than a dedicated, validated checkout endpoint
16 | Checkout & Payments | Real Payment Gateway (Razorpay/Stripe) | Live UPI/Card/NetBanking capture via a payment gateway SDK | Pending | High | No gateway package (razorpay/stripe) in Backend/package.json and no order-create or checkout routes found anywhere in server.js
17 | Checkout & Payments | Payment Webhook Signature Verification | Server verifies gateway signature before marking an order paid | Pending | High | POST /api/custom-orders/:id/pay sets payment_status='PAID' directly with no gateway callback or signature check — payment is not actually being captured or verified
18 | Checkout & Payments | GST & Hallmarking Charge Breakdown | Itemized display of jewelry GST and BIS hallmarking fee | Pending | Medium | No GST/hallmarking fields found in pricing logic or schema
19 | Checkout & Payments | Cash on Delivery (COD) Option | COD as an alternate payment method at checkout | Pending | Medium | No COD flag found in order schema or checkout routes
20 | Order Lifecycle | Orders Schema (dbo.orders) | Relational persistence of full order state | Completed | High | dbo.orders table with order_number, confirm, final_payable, payment_status fields
21 | Order Lifecycle | Admin Order Status Transitions | Admin can move orders through processing/accepted/rejected | Completed | High | PUT /api/admin/custom-orders/:id updates [confirm] status
22 | Order Lifecycle | Shipping Carrier API (AWB / Tracking) | Automated tracking-ID generation via Shiprocket/Delhivery etc. | Pending | Medium | No shipping/courier integration found in codebase
23 | Order Lifecycle | Automated Email Confirmations & Invoices | Order confirmation email + downloadable PDF invoice | Pending | Medium | No email package (nodemailer etc.) or PDF invoice generation found — only WhatsApp messaging exists
24 | Order Lifecycle | Returns & Refunds Portal | Self-service return/refund request workflow | Pending | Low | No routes or schema for returns found
25 | Admin Financial Analytics | Revenue / P&L Aggregation Endpoint | Server-side rollup of revenue, cost, labour, margin | Completed | High | GET /api/admin/analytics computes catalog & realized P&L, gross margin %, category profitability
26 | Admin Financial Analytics | Labour & Production Cost Tracking | Per-product labour cost factored into margin calculations | Completed | Medium | labour_cost column aggregated and subtracted from price in analytics query
27 | Admin Financial Analytics | Analytics Dashboard UI | Visual charts for admin (revenue, order success ratio) | Completed | Medium | Backend/public/analytics.html served at /admin/analytics
28 | Security & Infrastructure | SQL Injection Protection | All queries parameterized, no string-concatenated SQL | Completed | High | Verified — every query in server.js uses pool.request().input(...) parameter binding
29 | Security & Infrastructure | Secrets Management (.env) | No hardcoded credentials; example env template provided | Completed | High | Backend/.env in use + Backend/dist/.env.example template committed
30 | Security & Infrastructure | Restricted CORS Policy | API only accepts requests from approved frontend origins | Pending | High | app.use(cors()) is wide open with no origin whitelist — any site can call the API
31 | Security & Infrastructure | Security Headers (Helmet) | Standard HTTP security headers on every response | Pending | Medium | helmet is not in Backend/package.json dependencies
32 | Security & Infrastructure | API Rate Limiting | Throttling on auth/OTP and admin routes to block abuse | Pending | High | No express-rate-limit or equivalent found — OTP endpoints are unthrottled, open to spam/brute force
33 | Security & Infrastructure | Input Validation & Sanitization | Schema validation on all incoming request bodies | Pending | Medium | No express-validator/joi/zod found — request bodies passed straight to SQL params
34 | Security & Infrastructure | Automated Database Backups | Scheduled backups / point-in-time recovery for MSSQL | Pending | High | No backup automation found in repo — depends entirely on hosting provider configuration
35 | Frontend / UX | Responsive Storefront (Home/PLP/PDP) | Full storefront with hero, category grid, PDP gallery | Completed | High | HomePage.jsx, ProductListingPage.jsx, ProductDetailPage.jsx all present and wired via AppRouter
36 | Frontend / UX | Cart & Wishlist Drawers | Slide-out cart/wishlist with promo codes and quick-add | Completed | High | CartDrawer, WishlistDrawer, promo/coupon logic present in components
37 | Frontend / UX | Interactive Yatra/Mukhut Customizer | Visual studio for designing sacred/custom silver items | Completed | High | YatraCustomizerPage.jsx and CustomArtisanalOrderPage.jsx implemented
38 | Frontend / UX | Multi-Theme System | Switchable brand themes across the storefront | Completed | Low | 4 theme CSS files (aegean, lavender, nordic, sage) + ThemeContext.jsx
39 | Frontend / UX | SEO Metadata, OpenGraph & Schema.org | Dynamic per-page titles, meta tags, Product structured data | Pending | Medium | No react-helmet or schema.org/OpenGraph tags found in src/ or index.html
40 | Frontend / UX | Legal & Policy Pages | Privacy Policy, Terms of Service, Shipping & Refund Policy | Pending | Medium | Only a PolicyBadges.jsx trust-badge strip exists — no dedicated policy page content found
41 | Frontend / UX | Analytics & Conversion Tracking | GA4 / Meta Pixel purchase & funnel event tracking | Pending | Low | No GTM/GA4/Pixel snippets found in index.html
42 | Testing & DevOps | Automated Test Suite | Unit/integration tests for backend API and checkout logic | Pending | High | Backend package.json test script is the default stub: "echo Error: no test specified && exit 1" — no test files found
43 | Testing & DevOps | CI/CD Pipeline | Automated build/test/deploy on push | Pending | Medium | No .github/workflows or other CI config found in the repo
44 | Testing & DevOps | Production Build Pipeline | Reproducible frontend/backend build artifacts | Completed | Medium | vite build (frontend) + Backend/build_dist.js producing a deployable dist bundle/zip
45 | Testing & DevOps | Error Monitoring & Logging | Centralized error tracking (e.g. Sentry) in production | Pending | Medium | No monitoring/logging package found — errors only go to console.error
READINESS BY MODULE
| Domain / Module | Total | Completed | In Progress | Pending | Readiness %
| User Auth & Accounts | 5 | 2 | 0 | 3 | 40.0%
| Catalog & Inventory | 5 | 4 | 1 | 0 | 80.0%
| Custom Order & Quotation Workflow | 4 | 4 | 0 | 0 | 100.0%
| Checkout & Payments | 5 | 0 | 1 | 4 | 0.0%
| Order Lifecycle | 5 | 2 | 0 | 3 | 40.0%
| Admin Financial Analytics | 3 | 3 | 0 | 0 | 100.0%
| Security & Infrastructure | 7 | 2 | 0 | 5 | 28.6%
| Frontend / UX | 7 | 4 | 0 | 3 | 57.1%
Testing & DevOps